## Sheet1
ID | Task | Predecessor (Refer to ID) | Time estimates |  |  | Expected Time
|  |  | Optimistic (O) | Normal (M) | Pessimistic (P)
1 | Concept art for game assets | -
2 | Base Game Framework | -
3 | General Playboard set-up | 2
4 | Base Match 3 functions/mechanics | 3
5 | 2D Modeling | 1
6 | Battle Animations | 5
7 | Battle Mechanics | 4
8 | Battle Sequences | 6,7
9 | Player/Enemy Statistics | -
10 | Adaptive Difficulty | 4,8
11 | General In-Game Menu Layout & Design | 1
12 | In-Game Store | -
13 | Playboard editor | 3,5,12